## Agile
Sprint Number |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13
Sprint Start Date |  | 2021-03-09 | 2021-03-16 | 2021-03-23 | 2021-03-30 | 2021-04-06 | 2021-04-13 | 2021-04-20 | 2021-04-27 | 2021-05-04 | 2021-05-11 | 2021-05-18 | 2021-05-25 | 2021-06-01
Sprint End Date |  | 2021-03-16 | 2021-03-23 | 2021-03-30 | 2021-04-06 | 2021-04-13 | 2021-04-20 | 2021-04-27 | 2021-05-04 | 2021-05-11 | 2021-05-18 | 2021-05-25 | 2021-06-01 | 2021-06-08
Sprint Tasks | Sprint Task 1 | Set up a Project Plan | Model As-Is Process | Verify As-Is Process Model | Identify As-Is Improvements | Review As-Is Process | Model a To-Be Process | Verify To-Be Process | Iterate To-Be Process | Iterate To-Be Process | Describe the To-Be Process | Record and cut video | Finalized To-Be Process | Upload Deliverables on Github I 10.06.2021 - 07:59
| Sprint Task 2 | Learn to use Trello |  |  |  | Start on To-Be Process | Iterate As-Is Process | Get help with Integromat | Get help with Camunda | Debug Integromat |  | Process Mining | Redo video intro and outtro | Final Presentation I 10.06.2021
| Coaching | Coaching with Maja |  | Coaching with Maja | Iterate As-Is Process | Coaching with Devid |  | Coaching with Maja |  | Coaching with Maja | Testing | Coaching with Maja | Finalize Documentation
Tools Used |  | Excel, Trello |  |  |  |  | Integromat, Camunda | Postman, Camunda | Postman, Integromat, Camunda | Postman, Integromat, Camunda | Word, Powerpoint | Final Cut Pro, Loom, Rapidminer | Word / GitHub | GitHub

## Tabelle1
Projectplan
StartDate | 2021-03-04 | [7 empty] | 2021-03-06 | [6 empty] | 2021-04-03 | [8 empty] | 2021-05-01 | [9 empty] | 2021-06-05
Today | 2021-06-07 |  |  | Planned |  |  |  |  | 2021-03-06 | 2021-03-07 | 2021-03-13 | 2021-03-14 | 2021-03-20 | 2021-03-21 | 2021-03-27 | 2021-03-28 | 2021-04-03 | 2021-04-04 | 2021-04-10 | 2021-04-11 | 2021-04-17 | 2021-04-18 | 2021-04-24 | 2021-04-25 | 2021-05-01 | 2021-05-02 | 2021-05-08 | 2021-05-09 | 2021-05-15 | 2021-05-16 | 2021-05-22 | 2021-05-23 | 2021-05-29 | 2021-05-30 | 2021-06-05 | 2021-06-06 | 2021-06-12
Phase | Milestone | Task description | Tool | Startdate | Enddate | ToBe-Progress | AsIs-Progress | Gap | 2021-03-06 | 2021-03-07 | 2021-03-13 | 2021-03-14 | 2021-03-20 | 2021-03-21 | 2021-03-27 | 2021-03-28 | 2021-04-03 | 2021-04-04 | 2021-04-10 | 2021-04-11 | 2021-04-17 | 2021-04-18 | 2021-04-24 | 2021-04-25 | 2021-05-01 | 2021-05-02 | 2021-05-08 | 2021-05-09 | 2021-05-15 | 2021-05-16 | 2021-05-22 | 2021-05-23 | 2021-05-29 | 2021-05-30 | 2021-06-05 | 2021-06-06 | 2021-06-12
Phase 1 | Milestone | Kickoff |  | 2021-03-06 | 2021-03-06 |  |  | 0% | bar: 2021-03-06
As-Is Process |  | Define Project | None | 2021-03-06 | 2021-03-07 | 100% | 100% | 0% | bar: 2021-03-06 to 2021-03-07
|  | Set up a Project Plan | Excel | 2021-03-08 | 2021-03-13 | 100% | 100% | 0%
|  | Model a As-Is Process | Camunda | 2021-03-08 | 2021-03-21 | 100% | 100% | 0%
|  | Verify As-Is Process Model | Camunda | 2021-03-22 | 2021-03-28 | 100% | 100% | 0%
|  | Describe the As-Is Process and identify Improvements | Word | 2021-03-22 | 2021-03-28 | 100% | 100% | 0%
Phase 2 | Milestone | Finalized As-Is Process |  | 2021-03-28 | 2021-03-28 | bar: 2021-03-28
To-Be Process |  | Model a To-Be Process | Camunda | 2021-03-29 | 2021-04-04 | 100% | 100% | 0%
|  | Verify To-Be Process Model | Camunda | 2021-04-05 | 2021-04-18 | 100% | 100% | 0%
|  | Iterative Process Digitalisation | Postman, Integromat, Camunda | 2021-04-19 | 2021-05-21 | 100% | 100% | 0%
|  | Describe the To-Be Process | Word | 2021-05-17 | 2021-05-23 | 100% | 100% | 0% | bar: 2021-05-22 to 2021-05-23
|  | Testing |  | 2021-05-17 | 2021-05-23 | 100% | 100% | 0% | bar: 2021-05-22 to 2021-05-23
Phase 3 | Milestone | Finalized To-Be Process |  | 2021-05-23 | 2021-05-23 | bar: 2021-05-23
Presentation |  | Record process steps | Loom | 2021-05-24 | 2021-05-30 | 100% | 100% | 0% | bar: 2021-05-29 to 2021-05-30
|  | Cut sequences and integrate them into Presentation | Final Cut Pro | 2021-05-30 | 2021-05-30 | 100% | 100% | 0%
|  | Finalize Documentation | Word / GitHub | 2021-05-30 | 2021-06-06 | 100% | 100% | 0%
Phase 4 | Milestone | Final Prasentation / Deliverable
Presentation | Milestone | Final Prasentation I 10.06.2021 | PowerPoint | 2021-06-07 | 2021-12-12 | bar: 2021-06-12
Submission | Milestone | Upload Deliverables on Github I 10.06.2021 - 07:59 | GitHub | 2021-06-07 | 2021-12-12 | 0% | 100% | 100% | bar: 2021-06-12

## Rollup
Status | TaskOwner
Open | Ryan
In progress | Slavisa
finalized | Lukas
Robin
All